## Schedule
BS-Camp (Batch - 8) OJT Schedule
No | Date | Presentation
1 | 5 July 2025 (Sat) | Title, UseCase, ER diagram
2 | 12 July 2025 (Sat) | Documentation and Coding Development Progress
3 | 20 July 2025 (Sun) | Coding Development Progress
4 | 26 July 2025 (Sat) | Testing
5 | 2 August 2025 (Sat) | Testing and Pre-Project Presentation
6 | 9 August 2025 (Sat) | Project Presentation
No | Name | Title
1 | Myat Moe Pyae |  | kopyae135385@gmail.com
2 | Myo Thandar |  | thandarlwinpepe@gmail.com
3 | Nwae Nwae Win |  | nwaenwaewin2004@gmail.com
4 | Nyi Nyi Lwin | CO-MOVIE | nyinyilwin11.mm.com@gmail.com
5 | Sai Heart Han Onm | S-Music-Studio | sainaunt875@gmail.com

## S-Music-Studio
No | Date | Function | milestone | completed |  | Remark
1 | 2025-06-29 | Create Usecase Diagram | study (extend, include) |  | TRUE
2 | 2025-07-10 | Backend Code | All |  | TRUE

## nyinyi
No | Date | Function | milestone | completed |  | Remark
1 | 2025-06-29 | Create Usecase Diagram | study (extend, include) |  | TRUE
2 | 2025-07-12 | Coding (fornt end) | Dashboard, Home, Contact , Register , LogIn ,ForgetPassword |  | TRUE
3 | 2025-07-12 | Coding (fornt end) | Movies details |  | TRUE
4 | 2025-07-12 | Document | About of Website , Use Case and ERD |  | TRUE
5 | 2025-07-19 | coding (fornt end) and (backend) | Register, Sign In and other movie functions |  | TRUE
6
7
8
9
10

## Nwae Nwae
No | Date | Function | milestone | completed | Remark
1 | 2025-07-15 | backed Code | All | Yes

## Sample
No | Date | Function | milestone | completed |  | Remark
1 | 2023-06-29 | Create Usecase Diagram | study (extend, include) |  | FALSE